**ZSI –Summary of project activities**

**WP 1**

* Desktop research and analyses of relevant ethics aspects for Reinforce
* Clarification of data management and storage
* Reinforce Online Meeting
* Next step:
	+ A first draft of D1.2 by end of March
	+ Skype Calls with demonstrators if needed
	+ providing feedback for D1.1

**WP 2**

* Developed a template for task analysis
* Sent out a template to demonstrator partners to fill it in (deadline: 29th of February)
* So far received two filled-in templates (new particles at the LHC and Geoscience & Archeology), two still missing (gravitational wave noise hunting and deep sea hunters)
* Next steps:
	+ Calls with demonstrators to complete and finalize information
	+ Integration of results into D2.1 and WP 9 (fine-tuning of the logic model)

**WP 9**

* Logic model with output, outcomes and impact for Reinforce worked out based on the DoW
* Desk research on assessment strategies and instruments in citizen science projects
* Call with Grant on the practical implementation of the online survey in Zooniverse
* Next steps:
	+ fine-tuning of logic model per demonstrator
	+ a first outline of our Reinforce impact assessment strategy

**WP 10**

* Contribution to and review of ethics deliverable