## Slide 1
Definition of the legal steps to be taken and the permits to be obtained for the construction of the Einstein Telescope in the EMR region
SPB workshop – Maastricht – 25/01/23
Ph. Orban (with information from Amberg/Tractebel)

## Slide 2
Context
Large construction including underground and surface infrastructures
=> What rights are required to use the subsurface and the surface
=> What permits are required
Potential impacts during the construction and exploitation
=> What legislations must be respected?

## Slide 3
Context
Transboundary project
=> Different national (or even regional) legislations to consider

## Slide 4
Objectives
Mapping of public decisions and permits to acquire before start of civil engineering incl. related risks;
  Required studies
  Timeline to obtain permits
  Required permits
  Feasibility and associated risks
Mapping of private decisions and legal contracts to acquire before the start of civil engineering.
  Mapping of ownership relationship and right of use
  Ownership acquisition or usage right
  Feasibility and associated risks
Global timeline including the most important steps, decision moment and risks related to legal issues and permits;

## Slide 5
Partnership and organization
Association of two engineering compagnies and two lawyers' offices
Final meeting scheduled beginning of February 2023
Main assumptions :
  Focus on the Netherland, Flemish and Walloon region
  Large-scale study, not site specific

## Slide 6
Examples of deliverables
List of contractual agreements to be obtained before the start of civil engineering works (For each region/country)
 | Mode of acquisition | Duration | Extent of the right (ground/subground) | Characteristics (advantages, disadvantages, cost, ...)
Property rights |  |  |  | 
Co-ownership rights |  |  |  | 
Conventional easement |  |  |  | 
Legal easement |  |  |  | 
Usufruct |  |  |  | 
Emphyteusis right |  |  |  | 
Superficies |  |  |  | 
Example for private owner and the Walloon region

## Slide 7
List of public authorizations to be obtained and public procedures to be followed before the start of civil engineering works (For each region/country)
 | Scope of application (including possible exemption) | Competent authority | Procedure, including appeals | Criteria for the obtention | Timelines
Planning permit |  |  |  |  | 
Environmental permit |  |  |  |  | 
Heritage permit (German-speaking Community) |  |  |  |  | 
Authorization to derogate from the nature conservation law |  |  |  |  | 
Authorization to modify/create a municipal roadway |  |  |  |  | 
Authorization to modify/create a regional roadway |  |  |  |  | 
Domain authorization (municipal domain) |  |  |  |  | 
Domain authorization (regional domain) |  |  |  |  | 
Exploration or exploitation of underground resources permit |  |  |  |  | 
Soil quality control certificate |  |  |  |  | 
Ground control certificate |  |  |  |  | 
Obligations regarding the management of industrial waste |  |  |  |  | 
Authorization for the construction and operation of a gaseous products transport facility |  |  |  |  | 
Obligations regarding the safety of elevators |  |  |  |  | 
Obligations regarding the use of explosives |  |  |  |  | 
Authorization regarding electrical installations |  |  |  |  | 
Authorization regarding fire prevention and safety |  |  |  |  | 
Obligations related to the use of hazardous substances within the meaning of the cooperation agreement of 16/02/2016 (Seveso) |  |  |  |  | 
Authorization for exceptional transport |  |  |  |  | 
Expropriation in the public interest |  |  |  |  | 
Examples of deliverables

## Slide 8
List of public authorizations to be obtained and public procedures to be followed before the start of civil engineering works (For each region/country)
Examples of deliverables

## Slide 9
Global timeline : Engineering steps
Examples of deliverables
Opportunity Study
Due Diligence
Conceptual design
Tendering
Specifications of the project
Construction
Execution design
Construction
Identification of all stakeholders
Feasibility study
Master plan
Basic & Detailed design
Project design (depending on contract type)
Cost estimation & Schedule
Cost estimation & Schedule
Environmental and urbanistic permits
Call for tenders
Offer analysis and negotiation
Final acceptance
Acceptance of the works
As Built documentation
Tendering
Permitting
Construction
Opportunity Study
Due Diligence
Conceptual design
Tendering
Specifications of the project
Construction
Execution design
Construction
Identification of all stakeholders
Feasibility study
Master plan
Basic & Detailed design
Project design (depending on contract type)
Cost estimation & Schedule
Cost estimation & Schedule
Environmental and urbanistic permits
Call for tenders
Offer analysis and negotiation
Final acceptance
Acceptance of the works
As Built documentation
Tendering
Permitting
Construction
Permits files
Impact studies
Delivery of permits

## Slide 10
Global timeline : Engineering steps
Examples of deliverables
Opportunity study
Main goals:
  Identify needs and objectives of the project
  Identify specific requirements
  Define funding aspects and legal aspects
  Define what are the options to achieve the requirements
  Define the main geometry of the project

## Slide 11
Global timeline : Engineering steps - Feasibility study
Examples of deliverables
Main goals:
  Identify technical, geotechnical, urbanistic, environmental, legislative and financial constraints that will impact the project
  Analyse and compare different design options
  Decide on the most optimal solution
  Elaborate a master plan with a consolidated technical and financial analysis
  Also in this phase, Start thinking about contract type: Standard, D&B, PPP, etc.
~ 3 months
~ 4 months
~ 4 months

## Slide 12
Global timeline : Engineering steps - Basic and Detailed Design
Examples of deliverables
Main goals:
  Design the infrastructure
    Stability
    Environment
    Safety
    Construction details
  Deliverables:
    detailed plan views,
    detailed longitudinal profiles,
    detailed cross-sections,
    detail drawings,
    descriptive notes by discipline, with starting points, standards in effect, calculations and simulations, argumentation and conclusions,
    a detailed estimate of the investment cost
    a precise estimate of operating costs and revenues,
    timeframes for completion and phasing,
    expropriation plans.
~ 9 months

## Slide 13
Global timeline : Engineering steps - Urbanistic and environmental Permits
Examples of deliverables
Main goals:
  Obtain the permits based on the basic and detailed design
    Phase 1: Request
    Phase 2: Impact study (external)
    Phase 3: Updating design
    Phase 4: Permits delivrance
    …
~ 18-24 months

## Slide 14
Global timeline : Engineering steps - Tendering
Examples of deliverables
Main goals:
  Prepare call for tenders
    Technical aspects
    Admin aspects
  Define procurement strategy
  Prepare negotiation phase
  Publish RFQ & RFP
  Analyse offer and negotiate
  Awarding
~ 12 months
~ 9 months

## Slide 15
Global timeline
Examples of deliverables
From Feasibility Study to Start of Construction: between 3,5 and 4,5 years