## Slide 1: Request For Changes
How to manage changes in the ET Project
ET Symposium, Maastricht, May 7th 2024
Document ID | ET-0221A-24
Document type | Slides
Document status | RELEASED
Author | L. Latronico
Verified by | L. Orsini, L. Lucchesi, C. Olivetto
Approved by | A. Variola

## Slide 2: Outline
Context
Definitions
Flowchart
Discussion

## Slide 3: Context
We now operate in the ET Preparatory Phase
  R&D is ongoing
  Baseline design not yet established
  Many changes are expected
PO prepares to support the entire ET lifecycle with
  delivery of project documents (TDR, PMP, QAP…) to the BGR for approving ET
  Configuration Management during engineering, construction and integration
Changes must be managed to ensure quality, i.e. distribution of information and traceability

## Slide 4: Basic definitions
Change | Owner | Root system | Request For Change RFC | Change Control Board CCB
Deviation from released info or configuration (docs, specs, requirements, tech drawings) | Initiator and responsible of the management process | Physical or data system where the change originates | Process for instantiating a request of a change and seeking approval | Board of technical experts and relevant system managers to analyze and dispose (applies to major changes only)

## Slide 5: Main Change management steps
Identification and description
  Specifies nature, reason, owner and root system
Impact analysis and classification
  Defines which systems are affected
  Class is major if impact extends root system, else minor
Approval
  Evaluation of the impact
  Recommendation (approve/ reject/ re-analyze)
Validation
  Independent re-analysis of the approval process
Notification
  distribution of change-related information
Implementation
  Separate process not covered here

## Slide 6: RFC Flowchart
Identification
Description
Classification
Start of approval

## Slide 7: RFC Flowchart
Impact analysis

## Slide 8: RFC Flowchart
Validation
Notification
Implementation

## Slide 9: Discussion points
Documents support change process
  RFC
  Change evaluation report
  Many changes are expected
  Change Register
  Change notification
Key actors
  Change owner
  Root system manager
  Technical coordinator
Definition of boards (CCB, Validation) on a case-by-case basis
  shall ensure technical competence, independent and redundant evaluations
  As far as the validation processes are concerned, the relevant board and processes should be defined a priori, associated to the relevant roles.