## Slide 1: Progress on ET Pilot Sector and its future ET – CERN collaboration
Luigi SCIBILE on behalf of the ET-CERN Collaboration
XIV ET Symposium, Maastricht, 06-10 May 2024

## Slide 2
The main objectives are:
Coordinate the contributions of all parties involved in the study of ET beampipes.
Design, manufacture, assemble, and test a pilot sector of the selected ET beampipe vacuum systems.
Preparing and writing the ‘Technical Design Report’ for the vacuum systems of the ET’s arms, including cost estimations.
Contact and sharing of information with the Cosmic Explorer community.
CERN activities on ET beampipe vacuum
2019
2020
2021
2024
Collaboration
agreement
CERN-INFN-NIKHEF
Addendum on
CERN contribution to ET beampipes
Q4
Official start of the activities
IFAE joins the collaboration agreement
2023
2022
Q4
Start construction of the ET beampipe pilot sector
2025
Q4
Writing of TDR
Q3-Q4
Preliminary vacuum pipe TDR [ET-PP]
Q1 (January)
Peer review of the pilot sector
Courtesy of Carlo Scarcia

## Slide 3
Q1 2024 (January)
ET pilot sector
The pilot sector aims to test the design, fabrication, installation and commissioning of the proposed beampipes and support system. It also aims to compare the feasibility of a selected number of technical choices.
Project peer reviewed (international experts panel) with recommendations.
Q2-Q4 2024
Manufacturing and procurement of the ancillary components/equipment.
From Q4 2024/Q1 2025
Start of installation of a
AISI 441 VIRGO-like pipe Ø 1.08 m x 4 mm x 36 m
Courtesy of Carlo Scarcia

## Slide 4: ET Pilot sector - Organisation
Overall Coordination
Mechanical design team/ Integration
+
CERN design office
Post manufacturing Chemical cleaning
+
CERN’s surface finishing facility and chemical/surface analysis labs
Vacuum system and bakeout
+
CERN’s vacuum labs
Metallurgical analysis team
+
CERN’s metallurgy and mechanical measurement labs
Infrastructure, logistics and coordination
+
CERN’s site services
Fabrication team
+
CERN’s workshop and subcontracting service
Manufacturing
Suppliers
WP8
WP1
WP2
WP4
WP3
WP6
WP2
WP5
WP7

## Slide 5: ET pilot sector – Procurement and manufacturing
Manufacturing/Procurement
Materials and compontents procurement
ET Pilot sectors parts
Firm | Country
Witzenmann | DE
Skodock | DE
HKS | DE
Flexomat | DE
Teddington | GB
Bird bellows | GB
Heitz GmbH | DE
Kompaflex | CH
Klinger | DK
Firm | Country
CADINOX | ES
Alca Technologies | IT
CNIM | FR
VDL | NL
Firm | Country
Aperam | B
CERN workshops
CERN stores
CERN frame contract
AISI 441 Materials
Beampipe sections
Endcaps, Pumping modules
Support system
Bellows (AISI 316L)
Valves, pumps, instrumentation
Thermal insulation and Bakeout systems
Monitoring and control system
Assembled by CERN
CERN Stores
CERN frame contracts
Small orders

## Slide 6: ET pilot sector – Procurement and manufacturing
Manufacturing/Procurement
Materials and compontents procurement
ET Pilot sectors parts
Firm | Country
Witzenmann | DE
Skodock | DE
HKS | DE
Flexomat | DE
Teddington | GB
Bird bellows | GB
Heitz GmbH | DE
Kompaflex | CH
Klinger | DK
Firm | Country
CADINOX | ES
Alca Technologies | IT
CNIM | FR
VDL | NL
Firm | Country
Aperam | B
CERN workshops
CERN stores
CERN frame contract
AISI 441 Materials
Beampipe sections
Endcaps, Pumping modules
Support system
Bellows (AISI 316L)
Valves, pumps, instrumentation
Thermal insulation and Bakeout systems
Monitoring and control system
Assembled by CERN
CERN Stores
CERN frame contracts
Small orders
100%
100%
75%
End Q4-24
End Q4-24
End Q4-24
End Q1-25
End Q3-24

## Slide 7: ET pilot sector – Procurement and manufacturing
ET Pilot sectors parts
AISI 441 Materials
Endcaps, Pumping modules
Support system
Bellows (AISI 316L)
Valves, pumps, instrumentation
Thermal insulation and Bakeout systems
Monitoring and control system
Courtesy of M. Dakshinamurthy and A. T. Pérez
Beampipe sections

## Slide 8: ET pilot sector – Procurement and manufacturing
ET Pilot sectors parts
AISI 441 Materials
Beampipe sections
Support system
Bellows (AISI 316L)
Valves, pumps, instrumentation
Thermal insulation and Bakeout systems
Monitoring and control system
Endcaps, Pumping modules
Courtesy of G. Favre

## Slide 9: ET pilot sector – Procurement and manufacturing
ET Pilot sectors parts
AISI 441 Materials
Beampipe sections
Valves, pumps, instrumentation
Thermal insulation and Bakeout systems
Monitoring and control system
Endcaps, Pumping modules
Bellows (AISI 316L)
Support system
Courtesy of C. Garion, L. Gentini

## Slide 10: ET pilot sector – Procurement and manufacturing
ET Pilot sectors parts
AISI 441 Materials
Beampipe sections
Support system
Valves, pumps, instrumentation
Thermal insulation and Bakeout systems
Monitoring and control system
Endcaps, Pumping modules
Bellows (AISI 316L)
Courtesy of C. Garion

## Slide 11: ET pilot sector – Logistics
Courtesy of J. Hansen

## Slide 12: ET pilot sector – Logistics for step 1
Time
ET Pilot sectors parts
AISI 441 Materials
Beampipe sections
Endcaps, Pumping modules
Support system
Bellows (AISI 316L)
Valves, pumps, instrumentation
Thermal insulation and Bakeout systems
Monitoring and control system
Welding
PM
EC
PM
EC
Bellow
Bellow
Cleaning
Vacuum
firing
Cleaning
Alignment
Installation
Installation
Installation
Installation
Manufacturing/Procurement
Materials and compontents procurement
BAKEOUT
(Dimensions not to scale)
Measurements
STEP 1
1
Leak tests

## Slide 13: ET pilot sector – Logistics for STEP 2
Time
ET Pilot sectors parts
AISI 441 Materials
Beampipe sections
Endcaps, Pumping modules
Support system
Bellows (AISI 316L)
Valves, pumps, instrumentation
Thermal insulation and Bakeout systems
Monitoring and control system
Manufacturing/Procurement
Materials and compontents procurement
De-install instrumentation, valves and pumps
Measurements
STEP 2
(Dimensions not to scale)
PM
EC
PM
EC
Bellow
Bellow
2

## Slide 14: ET pilot sector – Logistics for STEP 3/4
Time
ET Pilot sectors parts
AISI 441 Materials
Beampipe sections
Endcaps, Pumping modules
Support system
Bellows (AISI 316L)
Valves, pumps, instrumentation
Thermal insulation and Bakeout systems
Monitoring and control system
Manufacturing/Procurement
Materials and compontents procurement
(Dimensions not to scale)
CUT
PM
EC
PM
EC
Bellow
Bellow
(Dimensions not to scale)
PM
EC
PM
EC
Bellow
Bellow
SPLIT

## Slide 15: ET pilot sector – Logistics for STEP 3&4
Time
ET Pilot sectors parts
AISI 441 Materials
Beampipe sections
Endcaps, Pumping modules
Support system
Bellows (AISI 316L)
Valves, pumps, instrumentation
Thermal insulation and Bakeout systems
Monitoring and control system
Re-install instrumentation, valves and pumps
Installation
Manufacturing/Procurement
Materials and compontents procurement
Welding
Alignment
PM
EC
PM
EC
Bellow
Bellow
BS
BS
BS
BS
BS
BS
Cleaning
Installation
BAKEOUT
(Dimensions not to scale)
Measurements
STEP 3
3
Measurements
STEP 4
4
Leak tests

## Slide 16
ET pilot sector – Main milestones
Q1, 2024
Q2, 2024
Q4, 2023
Q1, 2023
Q3, 2024
Q4, 2024
Q1, 2025
Q2, 2025
Q3, 2025
Q4, 2025
Q1, 2026
Q3, 2024 – Start installation of infrastructure
TT4 new location – to be prepared before installation.
29/02/2024 – Start the procurement process
OK for the Material – (see next slide)
Mid Q2 – Start manufacturing
On the critical path!!!
Mid/End Q4 – All procured parts @ CERN
Some parts on the critical path!!!
Except Pipe sectors ~ 2 months slac.
End Q4 – Tunnel ready for installation
On the critical path!!!
Mid Q1 2025 – Start vacuum measurement sequence
Planning for success!
Q3/Q4 – Preliminary vacuum pipe TDR [ET-PP]
Data available.
Courtesy of Carlo Scarcia

## Slide 17: ET pilot sector – Alignment
Contact established with CERN alignment and survey services.
Request for support during the installation sequence in TT4 (see also next slide):
  Trace the floor plan before installation of the supports
  Help with the alignment of the vacuum supports during installation
  Help with the alignment of vacuum chambers with respect to the end supports before welding.
  Check the position of the chambers when the system is under vacuum.
Started discussions for the alignment techniques for the 10km installation.

## Slide 18
April/May 2025 - Check the position of the chambers when the system is under vacuum and baked.
December 2024 - Geometrical verification of the chambers and baffles after fabrication and before installation.
October/November 2024 - Trace the floor plan based on an integration drawings
November 2024 - Help with the alignment of the vacuum supports during installation
January 2024 + June 2025 - Align vacuum chambers with respect to a drawing before welding and after welding.
Second pipe non shown yet on the schedule
ET pilot sector – Alignment planning

## Slide 19: Interfaces/Interferences between the beampipe and the tunnel: cross section
    Space required for the supporting structure, for welding and future inspections (min 500mm), for gate valves, for pumping modules and related control units (depending on design installation).
    Fire fighting equipment (water - DN200 pipe?)
    Cable trays for communication equipment?
    Ventilation and smoke extraction?
    Presence of alcoves/enlargements?
    Minimum safety distance between tubes and wall?
800
1100
1100
800
500
2720
2180
1100
500
2720
800

## Slide 20: Interfaces/Interferences between the beampipe and the tunnel: cross section
Space required for sectional gate valves (DN1000)
800
1100
1565 (W+V) x 2751 (L +M) x 356 (P) mm
+ 140 mm (Q)

## Slide 21: ET – CERN to be proposed future scope extension
Test of beampipe other than AISI 441 4mm VIRGO-like.
Prepare the framework for other beampipe solutions to be tested in the same environment.
Purchase a gate valve and carry out the mechanical integration studies, the UHV caracterization inclusing the conditioning and outgassing rate measurements.
Workout the detailed integration with the civil engineering.
Study alignment techniques for the 10km assembly and installation and eventual optimisations of the support system.
Design of leak detection systems for the manufacturing, installation and final system.
Design the detailed procedures for the installation and commissioning in the final ET tunnel design.
Study for the control of dust during all assembly and installation processes.
Carry out the baffle material outgassing studies and its integration and alignment in the ET final tubes.
Open to discuss, via ETO, the possibility to carry out other type of tests.
Update the TDR and costing in line with general ET timeline.

## Slide 22
ET pilot sector: peer review recommendations
Recommendation | Action
Investigation on corrosion resistance of ferritic stainless steels (tunnel environmental conditions) | Contract with UGhent to be launched for comparative corrosion studies
Use pilot sector as testbed for extrapolation of ET leak detection | Methodologies and tooling under investigation
ET pilot sector to be used to test different insulation materials and solutions (installation, removal) | Contact with companies started
Implementation of large gate valves (DN1000+) to test thermal cycling, stroke cycling, treatments etc. | Planned in the extension of ET-CERN scope
Implementation of temperature control systems in selected building | ET pilot sector moved to TT4 tunnel – stable temperature.
Consider launching a parallel test on a corrugated chamber (perhaps through external contribution) | Planned in the extension of ET-CERN scope
See Carlo’s Presentation